## Sheet1
Risk Category | Risk Description | Probability of Occurrence | Probability Score | Seriousness of Effects | Effect Seriousness Score | Matrix Scroe | Priority | Ranking | Strategies | Status
Organizational | The organisation is restructured so that different management are responsible for the project. | High | 0.7 | High | 0.8 | 0.56 | High | 1 | Prepare brieft presentation and detailed document for management showing how the project is progressing and making a very important contribution to the goals of the business. Keet effective and frequent communication with the new management team.
People | It is impossible to recruit staff with the skills required for the project. | High | 0.7 | High | 0.8 | 0.56 | High | 1 | Alert customer of potential difficulties and the possibility of delays timely, investigate buying-in components efficiently.
Estimation | Team may underestimate the cost beforehand and thus do not have enough budget during the development. | Moderate | 0.5 | High | 0.8 | 0.4 | High | 2 | The team should have a detailed budget. Instead of having a general one, the budget should be broken down into small components and each component should be analyzed and forecasted with reasonable cost.
People | Experienced staff will leave the project before it is finished. | Moderate | 0.5 | High | 0.8 | 0.4 | High | 2 | Reorganise team so that there is more overlap of work and people therefore understand each other’s jobs.
People | Key staff are ill at critical times in the project. | Moderate | 0.5 | High | 0.8 | 0.4 | High | 2 | Reorganise team so that there is more overlap of work and people therefore understand each other’s jobs. If the situation is urgent, invite experienced staff from other teams to contribute.
Requirements | Changes to requirements that require major design rework are proposed. | Moderate | 0.5 | High | 0.8 | 0.4 | High | 2 | Derive traceability information to assess requirements change impact, maximise information hiding in the design.
Technology | Software components that should be reused contain defects which limit their functionality. | Moderate | 0.5 | High | 0.8 | 0.4 | High | 2 | Replace potentially defective components with bought-in components of known reliability.
Technology | The database used in the system cannot process as many information per second as expected. | Moderate | 0.5 | High | 0.8 | 0.4 | High | 2 | Investigate the possibility of buying a higher- performance database.
Estimation | The time required to develop the software is underestimated. | High | 0.7 | Tolerable | 0.5 | 0.35 | High | 3 | More research and analysis should be taken before the start of development. All team members should have discussion together about the schedule, to make sure appropriate plan have been made. Investigate buying in components, investigate use of a program generator.
Estimation | The size of the software is underestimated. | High | 0.7 | Tolerable | 0.5 | 0.35 | High | 3 | More research and analysis should be taken before the start of development. All team members should have discussion together about the software complexity to make sure appropriate estimation about hte software size have been made. Investigate buying in components, investigate use of a program generator.
Requirements | Gap between Requirements And Developed Functionality It is possible that the functions developed by the team cannot match the requirements elicited beforehand. | High | 0.7 | Tolerable | 0.5 | 0.35 | High | 3 | Requirements should be realistic and appropriate. Thus more analysis and discussion should be taken beforehand. Requirement documents should be reviewed regularly during the development to ensure that crucial requirements are matched.
Tools | WebRTC (Real-time Communication) tools cannot be integrated. | High | 0.7 | Tolerable | 0.5 | 0.35 | High | 3 | More research and analysis should be taken before the start of development. Experienced developers should examine the integration ability of WebRTC. If the result is not favorable, use alternative tools.
Estimation | The rate of defect repair is underestimated. | Moderate | 0.5 | Tolerable | 0.5 | 0.25 | Intermediate | 4 | Replace potentially defective components with bought- in components of known reliability.
People | Human Error Team members may make some mistakes accidently during the whole process of the project. These mistakes may cause data inconsistency, system errors and project delay. | Moderate | 0.5 | Tolerable | 0.5 | 0.25 | Intermediate | 4 | In order to avoid mistakes, every team member should do review for the work done. Peer review should also be adopted, especially for crucial part of the project.
Requirements | Customers fail to understand the impact of requirements changes. | Moderate | 0.5 | Tolerable | 0.5 | 0.25 | Intermediate | 4 | Emphasis the meaningness of requirements changes by onsite demo, onsite trial and other methods that let customers have a real experience using the product.
Technology | The underlying technology on which the system is built is superseded by new technology. | Moderate | 0.5 | Tolerable | 0.5 | 0.25 | Intermediate | 4 | Before the project starts, techonology used should be examined with extensibility and future trend. If new techonology superseded the used techonology, examine the probability for replaceing including a cost-benefit analysis.
Tools | Real-time Communication tools which support the project do not perform as anticipated | Moderate | 0.5 | Tolerable | 0.5 | 0.25 | Intermediate | 4 | More research and analysis should be taken before the start of development. Experienced developers should examine the functionalities of WebRTC. If the result is not favorable, use alternative tools.
Estimation | Specifications of essential interfaces are not available on schedule. | Low | 0.3 | High | 0.8 | 0.24 | Intermediate | 5 | Investigate the reasons that cause the delay. Send more experienced staff to speed up the interface specification process.
Organizational | Organisational financial problems force reductions in the project budget. | Low | 0.3 | High | 0.8 | 0.24 | Intermediate | 5 | Prepare brieft presentation and detailed document for management showing how the project is progressing and making a very important contribution to the goals of the business.
Tools | Hardware that is essential for the project will not be delivered on schedule. | Low | 0.3 | High | 0.8 | 0.24 | Intermediate | 5 | Keep in contact with suppliers about delivery details and show great emphasis on the timely delivery. If the hardward is not delivered online, reschedule the hardware-relevant procedures to minimize the impact.
Organizational | There will be a change of organisational management with different priorities. | Low | 0.3 | Tolerable | 0.5 | 0.15 | Low | 6 | Currently unavaliable due to low priority
People | Required training for staff is not available. | Low | 0.3 | Tolerable | 0.5 | 0.15 | Low | 6 | Currently unavaliable due to low priority
Tools | The code generated by Real-time Communication tools is inefficient. | Moderate | 0.5 | Low | 0.2 | 0.1 | Low | 7 | Currently unavaliable due to low priority